## Features
Feature ID | Feature Name | Feature Description | Initial Estimate
0 | Login Pane
1 | Dealer Pane
2 | Card Rendering / Player Pane
3 | Button methods
4 | Pane swapping
5 | Artistics bits LoginPane
6 | Get card images.
7 | Deck of cards class
8 | Hand class
9 | Card rendering / middle node / player pane
10 | Driver / game play
11 | Player class with player name with points
12 | Save data with name and points ( stores player objects )
13 | Player List, can find users by name.
14 | Define ante, win, tie methods for players.
15 | Create and update project outline and sprint log

## Sprint 1
Sprint Start Date | 2017-10-30
Sprint End Date | 2017-11-20
Related Feature | Task name | Task Description | Task Estimate | Task Actual | Assigned To
Figure out this Trello notepad stuff | Figure out this Trello notepad stuff | Learning to use Trello for project and task management | 30min | 30 min | All
| Created a GitHub repository for all out code and documents. | Created a GitHub repository for all out code and documents. | 30 min | 30 min | All

## Sprint 2
Sprint Start Date | 2017-11-01
Sprint End Date | 2017-11-06
Related Feature | Task name | Task Description | Task Estimate | Task Actual | Assigned To
| Created all cards for each team member’s part. | Created all cards for each team member’s part. | 30 min | 30 min | All
| GUI design | GUI design. | 2hrs | 2hrs | Brandon
| Player and game data management. | Player and game data management | 2hrs | 2hrs | Wilson
| Driver and game engine. | Driver and game engine. | 2hrs | 2hrs | Max
| Assigned preliminary due dates for all cards. | Assigned preliminary due dates for all cards. | 10 min | 10 min | All

## Sprint 3
Sprint Start Date | 2017-10-23
Sprint End Date | Date of Sprint End
Related Feature | Task name | Task Description | Task Estimate | Task Actual | Assigned To
test feature name
Initial planning | Initial project preparation/beginning |  | 1hr | 1hr | all
Sprint Start Date | 2017-11-06
Sprint End Date | 2017-11-08
Related Feature | Task name | Task Description | Task Estimate | Task Actual | Assigned To
|  |  | 30 min | 30 min | All
| Work on GUI design | GUI design. | 2hrs | 2hrs | Brandon
| Work on player and game data management. | Player and game data management | 2hrs | 2hrs | Wilson
| Work on Driver and game engine. | Driver and game engine. | 2hrs | 2hrs | Max

## Sprint 4
Sprint Start Date | 2017-11-09
Sprint End Date | 2017-11-13
Related Feature | Task name | Task Description | Task Estimate | Task Actual | Assigned To
| Continue work on GUI design | GUI design. | 2hrs | 2hrs | Brandon
| Continue work on Player and game data management. | Player and game data management | 2hrs | 2hrs | Wilson
| Continue work on Driver and game engine. | Driver and game engine. | 2hrs | 2hrs | Max

## Sprint 5
Sprint Start Date | 2017-11-13
Sprint End Date | 2017-11-16
Related Feature | Task name | Task Description | Task Estimate | Task Actual | Assigned To
| Continued work on GUI design | GUI design. | 2hrs | 2hrs | Brandon
| Continued work on Player and game data management. | Player and game data management | 2hrs | 2hrs | Wilson
| Continued work on Driver and game engine. | Driver and game engine. | 2hrs | 2hrs | Max

## Sprint 6
Sprint Start Date | 2017-11-17
Sprint End Date | 2017-11-20
Related Feature | Task name | Task Description | Task Estimate | Task Actual | Assigned To
| Integrade GUI, Player and Game Engine | Integrade all code, debug and test. | 2hrs | 4hrs | All

## Sprint 7
Sprint Start Date | 2017-11-21
Sprint End Date | 2017-11-22
Related Feature | Task name | Task Description | Task Estimate | Task Actual | Assigned To
| Test and Debug | Test and Debug | 4hrs | 4hrs | All
| Finalize project outline and sprintLog | Project Outline and Sprint Log | 2hrs | 2hrs | Wilson